## GanttChart
Gantt Chart
Converge Business Blockchain
| Project Start Date | 2022-04-10 |  |  |  | Display Week | 1 |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10
| Project Lead | Alex Greig | [6 empty] | 2022-04-11 | [6 empty] | 2022-04-18 | [6 empty] | 2022-04-25 | [6 empty] | 2022-05-02 | [6 empty] | 2022-05-09 | [6 empty] | 2022-05-16 | [6 empty] | 2022-05-23 | [6 empty] | 2022-05-30 | [6 empty] | 2022-06-06 | [6 empty] | 2022-06-13
 | time axis 2022-04-11 to 2022-06-19
WBS | TASK |  | PREDECESSOR | START | END | DAYS | % DONE | WORK DAYS | time axis 2022-04-11 to 2022-06-19
1 | Research and Idea Generation |  |  |  | - |  |  | -
1.1 | Generation of Ideas and final selection of Idea. Research surrounding the technologies that would facilitate the developent of the software solution and the way in which the project could be completed. |  |  | 2022-04-10 | 2022-04-19 | 10 | 100% | 7
2 | Design and Project Documentation |  |  |  | - |  |  | -
2.1 | Gantt Chart |  |  | 2022-04-19 | 2022-04-22 | 4 | 100% | 4
2.1.1 | Problem statement and envisioned solution and how it will function. |  |  | 2022-04-22 | 2022-04-25 | 4 | 100% | 2
2.1.2 | Issues relative to the program |  |  | 2022-04-25 | 2022-04-29 | 5 | 100% | 5
2.2 | Interface Design |  |  | 2022-04-29 | 2022-05-06 | 8 | 100% | 6
2.3 | Quality Assurance Criteria |  |  | 2022-05-06 | 2022-05-09 | 4 | 100% | 2
2.4 | Feasibility Study |  |  | 2022-05-09 | 2022-05-14 | 6 | 100% | 5
2.5 | Algorithms |  |  | 2022-05-14 | 2022-05-22 | 9 | 100% | 5
3 | Development |  |  |  | - |  |  | -
3.1 | Develop underlying blockchain using substrate framwork. Making sure WASM runtime, RPC Calls, P2P Networking, Consensus and storage modules work in unison to create the business blockchain |  |  | 2022-05-22 | 2022-05-29 | 8 | 100% | 5
3.2 | Develop the Frontend of the system using ReactJS, Webassembly and Remote Procedure Calls to access the blockchain from the client. Create a html, css and javascript webfront that can be accessed by clients to manage transactions. |  |  | 2022-05-29 | 2022-06-03 | 6 | 100% | 5
3.3 | Ability for Businesses to mint and trade non-fungiable tokens which are digital representations of non-fungiable assets in physical world. These could be contracts, invoices, labour with certain terms. |  |  | 2022-06-03 | 2022-06-08 | 6 | 100% | 4
3.4 | Ability for Businesses to mint fungiable tokens which are digital representations of fungiable assets in the physical world. This type of tokenisation would be heavily used in supply chain managements and for supply chain partner transactions. Assets could include computers, diamonds, gold or even produce like apples. |  |  | 2022-06-08 | 2022-06-12 | 5 | 100% | 3
3.5 | Implementation of Procure-to-Pay and Quote to cash. Utilising the intrinsic logic of the blockchain runtime and smart contracts to facilitate automated trading. |  |  | 2022-06-12 | 2022-06-16 | 5 | 100% | 4
3.6 | Automated document creation or statistics that show accounts payable and recieveable, also providing documents aiding in auditing and the complex taxation processes. |  |  | 2022-06-16 | 2022-06-19 | 4 | 100% | 2
3.7 | Zero Knowledge Proofs to make the transactions more private and private information isn't widely shared across the blockchain. |  |  | 2022-06-19 | 2022-06-21 | 3 | 100% | 2
3.8 | Smart Contracts that better facilitate the transfer of assets between companies. Also enable companies to create their own automated contracts for procurement and other financial processes. |  |  | 2022-06-21 | 2022-06-22 | 2 | 100% | 2
4 | Testing & Meetings with Clients |  |  |  | - |  |  | -
4.1 | Meeting with CFO Mr Fong for continuous communication surrounding project timeline. |  |  | 2022-05-10 | 2022-06-21 | 43 | 100% | 31
4.2 | Modular and Systematic testing of software |  |  | 2022-06-21 | 2022-06-22 | 2 | 100% | 2
5 | Theory Work |  |  |  | - |  |  | -
5.1 | Logbook |  |  | 2022-04-10 | 2022-06-21 | 73 | 100% | 52
5.2 | Showcase Video |  |  | 2022-06-17 | 2022-06-21 | 5 | 100% | 3
Note on A7: Work Breakdown Structure Level 1: 1, 2, 3, ... Level 2: 1.1, 1.2, 1.3, ... Level 3: 1.1.1, 1.1.2, 1.1.3, … - The WBS uses a formula to control the numbering, but the formulas are different for different levels. Copy and Paste the cells in the WBS column from the examples at the bottom of the worksheet.
Note on B7: Task Description Enter the name of each task and sub-task. Use indents for sub-tasks.
Note on C7: Task Lead Enter the name of the Task Lead in this column.
Note on D7: Predecessor Tasks: You can use this column to enter the WBS of a predecessor for reference. The PRO version uses formulas to automatically calculate the Start Date based on the Predecessor.
Note on E7: Task Start Date You can manually enter the Start Date for each task or use a formula to create a dependency on a Predecessor. For example, you could enter =enddate+1 to set the Start date to the next calendar day, or =WORKDAY(enddate,1) to set the Start date to the next work day (excluding weekends), where enddate is the cell reference for the End date of the Predecessor task.
Note on F7: End Date: The End Date is calculated based on the Start Date and the Calendar Days columns.
Note on G7: Duration (Calendar Days) The duration is the number of calendar days for the given task. The duration is calculated as the End Date minus the Start Date plus 1 day, so that a task starting and ending on the same day has a duration of 1 day. Note: The conditional formatting used to create the gantt chart references this column.
Note on H7: Percent Complete Update the status of this task by entering the percent complete (between 0% and 100%).
Note on I7: Work Days Counts the number of work days, excluding the weekends (Saturday and Sunday). In the PRO version, you can customize the work week and list specific non-working days like holidays. In the PRO version, the default input is the Work Days instead of the Calendar Days.